## Things to be aware of
Actions
Meeting | Responsibility | Action | Deadline | Status | Notes
| AH | Defib checks?
grass cutting
|  | Hedges |  |  | Frequency of cuts?
|  | Rents requested in April each year |  |  | Bowls, HSRC, Netball, football
|  | Solar farm monies invoice |  |  | April annually
Insurance quotes for next October
| JB | Area board meetings
| AH | LHFIG meetings
| NF | Annual footpath survey

## Councillor jobs
Actions
Meeting | Responsibility | Action | Deadline | Status | Notes
October | RG | To liaise with Steve Morris re: walking map |  | Ongoing
| JF | Draft facilities budget | 2025-01-01 | Ongoing
| GB | Draft precept | 2025-12-01 | Ongoing
| SS | Consider cleks salary |  | Ongoing
| CW | send ROSPA report to clerk |  | Complete | Received 14/11/24
| KL | Neighbourhood Plan - Consultation ion December | December | Ongoing
| ALL | Recruit 3 more councillors for election |  | Ongoing
| JF | JF to contact safari supper re: donation |  | Ongoing
| LW | HPC website; to agree a plan of action | December | Ongoing
July | LW | What 3 words for bug hotel |  | Ongoing
July | AH | Hawcroft improvement for LHFIG |  | Ongoing
| SS | S106 monies - how to be spent |  | Ongoing
| SS | Speedbot data |  |  | Working with volunteer; check in New Year on progress.

## Admin
Admin/Clerk Actions
Meeting | Responsibility | Action | Deadline | Status | Notes
Every month |  | Send village report to Parish Steward
Type minutes
Type report for magazine
Digital filing
Pay invoices
Check for training opportunitys for councillors & clerk
October | GB | Speak with National Trust re: Walking map |  | Ongoing
| GB | Speak with National Trust re: rear of garden |  | Ongoing | Emailed 11/01, 10/05, 09/10, and 14/11
| GB | Seek advice from WALC re: Bowls club |  | Ongoing
| GB | Little Parks open space - liaise with Wilts Council |  | Ongoing
| GB | Book Operation London Bridge training |  | Complete
| GB | Draft report from Operation London Bridge training |  | Ongoing | Training held on 28/11 - Training cancelled - rebook.
| GB | Draft precept | 2025-12-01 | Ongoing
| GB | Forward village inspection report to Parish Steward |  | Ongoing
| GB | To liaise with the village hall re: meetings downstairs |  | Ongoing | Upstairs room is often disrupted by downstairs meetings. Also not very accessible.
| GB | Call Solicitors to confirm they hold no documents |  | Ongoing | Spoke 04/09; they would call back if they held papers
| GB | Go over previous minutes to back fill outstanding actions |  | Ongoing
| GB | Type Extraordinary minutes |  | Ongoing
| GB | Draft / get approval for polies |  | Ongoing
| GB | Apply for LCAS award |  | Ongoing
| GB | Find dates for Area Board and LHFIG meetings |  | Ongoing
| GB | Order Freedom scroll |  | Complete | Ordered; waiting for invoice
|  | Let Ian Bolden know when white lines will be installed. |  |  | boldenian@gmail.com

## Highways
Highways actions
Meeting | Responsibility | Action | Deadline | Status | Notes
October |  | Little Parks roadblock - Take to LHFIG |  | Ongoing
October | SS | Speedbot - recruit a volunteer |  | Complete
| AH | Road names for Bewley

## Longer term
Longer term
Meeting | Responsibility | Action | Deadline | Status | Notes
2024-07-03 | SS | Clearance of ditch at Copse Farm |  | Ongoing
2024-07-03 |  | Improvements to highway safety for school children |  | Ongoing | Needs action by school
2024-09-11 |  | Damaged railings Ham Green |  | Ongoing | Highways not fixing - raise complaint or get Hiscox to do it
2024-09-11 | SS | Future of the B3106 Staverton Lane |  | Ongoing
2024-09-11 | GB | Register Rec with Land Registry |  | Ongoing | Locate deeds
2024-09-25 |  | Flood gates close/open |  | Ongoing
2024-09-25 |  | Re-surface The Street |  | Ongoing
2024-10-10 |  | Post bylaw on rec |  | Ongoing
2024-10-10 | GB | Take ownership of Little Parks green |  | Ongoing
2024-10-10 |  | Ownership of shelter |  | Ongoing

## Lists
SS | Complete
RG | Ongoing
JF | On hold
AH
NF
JB
LW
KL
CW
ALL
GB
TC